Project Plan

<Project Name>

Student Names

Table of Contents

[1.0 Introduction 3](#_Toc46748287)

[1.1 Problem Background 3](#_Toc46748288)

[1.2 Scope 3](#_Toc46748289)

[1.3 Document contents 3](#_Toc46748290)

[2.0 Work Breakdown Structure 4](#_Toc46748291)

[3.0 Activity Definition & Estimation 5](#_Toc46748292)

[4.0 Gantt Chart 6](#_Toc46748293)

# Introduction

## Background

The Victoria State Accident Dataset is a large and complex dataset that contains information on road accidents that occurred in Victoria, Australia from 2015 to 2020. The dataset includes information on the type of accident, the location, the time of day, the weather conditions, and the number of injuries and fatalities. The dataset is a valuable resource for traffic engineers, urban planners, and other stakeholders who are responsible for improving road safety. However, the sheer size and complexity of the dataset make it difficult to extract meaningful insights from it. This project aims to develop a software solution that will make it easier to analyse the Victoria State Accident Dataset. The software will provide users with a variety of tools for data cleaning, data mining, and data visualization. This will allow users to identify patterns and trends in the data that would be difficult to see by simply looking at the raw data.

## Scope

The project's scope is comprehensive and designed to meet a range of essential requirements. At its core, the project will design, develop, and deploy a specialized software tool tailored to analyse the Victoria State Accident Dataset. The software will feature an intuitive user interface to ensure ease of use for a diverse user base, ranging from traffic engineers to local authorities. Robust data filtering tools will be incorporated to allow users to sift through the extensive dataset effectively, focusing on specific variables like regions, accident types, and time frames. Additionally, the software will offer a variety of data visualization options, including heatmaps, line graphs, and bar charts, to facilitate better understanding and interpretation of the data. Lastly, predictive analysis capabilities will also be integrated, enabling stakeholders to forecast future accident trends and thereby engage in proactive planning. This comprehensive approach ensures that the software not only serves as an analytical tool but also as a decision-making platform for various stakeholders.

## Document contents

* **Project Plan.docx**: This document outlines the project's Introduction, Work Breakdown Structure, Activity Definition and Gantt Chart.
* **Software Design Document.docx**: A detailed document describing the software architecture, components, and data flow.
* **Gantt chart.xlsx**: A high-resolution Gantt chart illustrating the project timeline and milestones.
* **Executive Summary.docx**: A concise document summarising the project's objectives, key features, and expected outcomes.
* **git\_log.txt**: A copy of the Git Log to track version control and changes.
* **Interface.fbp**: A file containing the image of wxFormBuilder.
* **use case diagram.png**: A visual representation of the software's use cases.
* **FlowChart.png**: A flowchart depicting the software's functional workflow.
* **README.md**: A markdown file providing an overview and instructions for the project.


*Include some background information about the problem, the scope and what this document will contain.*

# Work Breakdown Structure

*This section should include the work breakdown structure for the whole project. The elements from the WBS should be used to generate your activity definition and those activities should then be scheduled in the Gantt Chart. Remember to consider ALL project activities – anything you do or will need to do should be included in the WBS*

*WBS’s are usually presented as some kind of hierarchical diagram/chart etc. The details what is involved each work unit should be provided in section 3:* ***Activity Definition***

*You do NOT need to do a WBS Dictionary for this project – the activity definition (whilst slightly different) will suffice. The WBS is focussed on SCOPE. The Activity definition is focussed on TIME.*



# Activity Definition & Estimation

*From your WBS, define the activities required for your project. You will revise this document and add more detail for part B as you discover more about the project.*

*Each activity should be clearly identified by a number and should match up to your Gantt chart. You should provide some estimations for the time you think each activity will take. This should make it easy to prepare your Gantt chart.*

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Task ID** | **Description** | **Effort** | **Resources** | **Predecessor** |
| Project Initiation | | | | |
| 1 | Develop Project Documents | 1 day | Project Manager, Business Analyst | 0 |
| 2 | Develop WBS | 2hrs | Project Manager, Project Team | 1 |
| 3 | Identify Stakeholders | 1hr | Project Manager, Project Team | 1 |
| 4 | Define Initial Scope Statement | 2hrs | Project Manager, Business Analyst | 1 |
| Requirements and Analysis | | | | |
| 5 | Gather User Requirements | 1 hr | Business Analyst, Data Scientist | 3,4 |
| 6 | Document Software Requirements | 1 hr | Business Analyst, Software Architect | 5 |
| 7 | Create Use Case Diagrams | 1 hr | Business Analyst, UI/UX Designer | 5 |
| Design Tasks | | | | |
| 8 | Design System Components | 3 hrs | Software Architect, System Designer | 6,7 |
| 9 | Develop User Interface Wireframes | 3 hrs | UI/UX Designer | 8 |
| 10 | Design Visualization Components | 3 hrs | UI/UX Designer, Data Analyst | 8 |
| 11 | Design Predictive Analysis Algorithm | 2 hrs | Datta Analyst, Software Developer | 8 |
| Development Tasks | | | | |
| 12 | Backend: Develop Data Handling Module | 4 hrs | Software Developer, Data Analyst | 10 |
| 13 | Backend: Implement Data Filtering | 4 hrs | Software Developer, Data Analyst | 12 |
| 14 | Frontend:  Implement User Interface | 3 hrs | Software Developer, UI/UX Designer | 13 |
| 15 | Frontend: Develop Visualization Components | 3 hrs | Software Developer, Data Analyst | 10 |
| 16 | Develop Prediction Algorithm | 1 day | Data Scientist, Data Analyst | 13,15 |
| Testing Tasks | | | | |
| 17 | Conduct Unit Testing | 2 hrs | QA Testers, Software Developer | 12,13,14,15,16 |
| 18 | Perform Integration Testing | 2 hrs | QA Testers, Software Developer | 17 |
| 19 | User Acceptance Testing (UAT) | 2 hrs | QA Tester, Project Manager | 18 |
| Documentation | | | | |
| 20 | Create User Manual | 3 hrs | UI/UX Designer | 19 |
| 21 | Prepare Technical Documentation | 2 hrs | Software Architect | 16,19 |

*Should we include “Cost”? Include Updating Gantt chart?*

# Gantt Chart

*This section should contain your Gantt chart. The items in the Gantt chart should match the activity definition from section 3. You should also submit your Gantt chart file separately.*