## Project Planner
Data Analysis and Visualization Software for Accident Data
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68
1. Develop Project Documents | 2023-08-28 | 7 | 2023-08-28 | 6 | 100% | bar: PERIODS 1 to PERIODS 7
2. Develop WBS | 2023-08-30 | 2 | 2023-08-30 | 2 | 100% | bar: PERIODS 7 to PERIODS 9
3. Identify Stakeholders | 2023-08-28 | 1 | 2023-08-28 | 1 | 100% | bar: PERIODS 9 to PERIODS 10
4. Define Initial Scope Statement | 2023-08-30 | 1 | 2023-08-30 | 1 | 100% | bar: PERIODS 10 to PERIODS 11
5. Update Gantt Chart | 2023-08-28 | 2 | 2023-08-28 | 1 | 100% | bar: PERIODS 11 to PERIODS 13
6. Gather User Requirements | 2023-08-30 | 1 | 2023-08-30 | 1 | 100% | bar: PERIODS 12; PERIODS 14
7. Document Software Requirements | 2023-08-28 | 1 | 2023-08-28 | 1 | 100% | bar: PERIODS 13; PERIODS 15
8. Create Use Case Diagram | 2023-08-28 | 1 | 2023-08-28 | 1 | 100% | bar: PERIODS 14; PERIODS 16
9. Design System Components | 2023-08-29 | 4 | 2023-08-29 | 4 | 100% | bar: PERIODS 15 to PERIODS 20
10. Develop User Interface Wireframes | 2023-08-29 | 3 | 2023-08-29 | 3 | 100% | bar: PERIODS 19 to PERIODS 23
11. Design Visualization Components | 2023-08-29 | 3 | 2023-08-29 | 2 | 100% | bar: PERIODS 22 to PERIODS 26
12. Design Predictive Analysis Algorithm | 2023-08-29 | 2 | 2023-08-29 | 2 | 100% | bar: PERIODS 24 to PERIODS 25; PERIODS 27 to PERIODS 28
13. Implement Data Analysis Program | 2023-09-23 | 1 | 2023-09-25 | 1 | 100% | bar: PERIODS 26; PERIODS 29
14. Backend: Develop Data Handling Module | 2023-09-28 | 4 | 2023-09-28 | 2 | 100% | bar: PERIODS 27 to PERIODS 28; PERIODS 30 to PERIODS 33
15. Backend: Implement Data Filtering | 2023-09-28 | 4 | 2023-09-28 | 2 | 100% | bar: PERIODS 29 to PERIODS 30; PERIODS 34 to PERIODS 37
16. Frontend: Implement User Interface | 2023-09-28 | 3 | 2023-09-28 | 2 | 100% | bar: PERIODS 31 to PERIODS 32; PERIODS 38 to PERIODS 40
17. Frontend: Develop Visualization Components | 2023-09-28 | 3 | 2023-09-28 | 2 | 100% | bar: PERIODS 33 to PERIODS 34; PERIODS 41 to PERIODS 43
18. Develop Prediction Algorithm | 2023-09-28 | 7 | 2023-09-28 | 4 | 100% | bar: PERIODS 35 to PERIODS 38; PERIODS 44 to PERIODS 50
19. Conduct Unit Testing | 2023-10-04 | 2 | 2023-10-04 | 2 | 100% | bar: PERIODS 39 to PERIODS 40; PERIODS 51 to PERIODS 52
20. Perform Integration Testing | 2023-10-04 | 2 | 2023-10-04 | 2 | 100% | bar: PERIODS 41 to PERIODS 42; PERIODS 53 to PERIODS 54
21. User Acceptance Testing(UAT) | 2023-10-04 | 2 | 2023-10-04 | 2 | 100% | bar: PERIODS 43 to PERIODS 44; PERIODS 55 to PERIODS 56
22. Create User Manual | 2023-10-04 | 3 | 2023-10-04 | 3 | 100% | bar: PERIODS 45 to PERIODS 47; PERIODS 57 to PERIODS 59
23. Generate Testing Report | 2023-10-04 | 2 | 2023-10-04 | 2 | 100% | bar: PERIODS 48 to PERIODS 49; PERIODS 60 to PERIODS 61
24. Prepare Technical Documentation | 2023-10-04 | 2 | 2023-10-05 | 2 | 100% | bar: PERIODS 50 to PERIODS 51; PERIODS 62 to PERIODS 63
25. Prepare Executive Summary | 2023-10-04 | 2 | 2023-10-07 | 2 | 100% | bar: PERIODS 52 to PERIODS 53; PERIODS 64 to PERIODS 65
26. Finalize Project Deliverables | 0510/2023 | 2 | 2023-10-05 | 1 | 100% | bar: PERIODS 54; PERIODS 66 to PERIODS 67
27. Closeout Meeting | 2023-10-06 | 1 | 2023-10-06 | 1 | 100% | bar: PERIODS 55; PERIODS 68