## Project Planner
Data Analysis and Visualization Software for Accident Data
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1. Develop Project Documents | 2023-08-28 | 7 | 2023-08-28 | 6 | 100% | bar: PERIODS 1 to PERIODS 7
2. Develop WBS | 2023-08-30 | 2 | 2023-08-30 | 2 | 100% | bar: PERIODS 7 to PERIODS 9
3. Identify Stakeholders | 2023-08-28 | 1 | 2023-08-28 | 1 | 100% | bar: PERIODS 9 to PERIODS 10
4. Define Initial Scope Statement | 2023-08-28 | 2 | 2023-08-28 | 1 | 100% | bar: PERIODS 10 to PERIODS 12
5. Gather User Requirements | 2023-08-30 | 1 | 2023-08-30 | 1 | 100% | bar: PERIODS 11; PERIODS 13
6. Document Software Requirements | 2023-08-28 | 1 | 2023-08-28 | 1 | 100% | bar: PERIODS 12; PERIODS 14
7. Create Use Case Diagram | 2023-08-28 | 1 | 2023-08-28 | 1 | 100% | bar: PERIODS 13; PERIODS 15
8. Design System Components | 2023-08-29 | 4 | 2023-08-29 | 4 | 100% | bar: PERIODS 14 to PERIODS 19
9. Develop User Interface Wireframes | 2023-08-29 | 3 | 2023-08-29 | 3 | 100% | bar: PERIODS 18 to PERIODS 22
10. Design Visualization Components | 2023-08-29 | 3 | 2023-08-29 | 2 | 100% | bar: PERIODS 21 to PERIODS 25
11. Design Predictive Analysis Algorithm | 2023-08-29 | 2 | 2023-08-29 | 2 | 100% | bar: PERIODS 23 to PERIODS 24; PERIODS 26 to PERIODS 27
12. Backend: Develop Data Handling Module | 2023-09-15 | 4 |  |  | 0% | bar: PERIODS 28 to PERIODS 31
13. Backend: Implement Data Filtering | 2023-09-15 | 4 |  |  | 0% | bar: PERIODS 32 to PERIODS 35
14. Frontend: Implement User Interface | 2023-09-11 | 3 |  |  | 0% | bar: PERIODS 36 to PERIODS 38
15. Frontend: Develop Visualization Components | 2023-09-11 | 3 |  |  | 0% | bar: PERIODS 39 to PERIODS 41
16. Develop Prediction Algorithm | 2023-09-15 | 7 |  |  | 0% | bar: PERIODS 42 to PERIODS 48
17. Conduct Unit Testing | 2023-09-22 | 2 |  |  | 0% | bar: PERIODS 49 to PERIODS 50
18. Perform Integration Testing | 2023-09-22 | 2 |  |  | 0% | bar: PERIODS 51 to PERIODS 52
19. User Acceptance Testing(UAT) | 2023-09-22 | 2 |  |  | 0% | bar: PERIODS 53 to PERIODS 54
20. Create User Manual | 2023-09-25 | 3 |  |  | 0% | bar: PERIODS 55 to PERIODS 57
21. Prepare Technical Documentation | 2023-09-25 | 2 |  |  | 0% | bar: PERIODS 58 to PERIODS 59